## Release Scoping
| Enter feature name, MoSCoW, and Effort (man days) | [5 empty] | Choose business and product strategy criteria and enter values for each feature | [6 empty] | 0-1 (boolean), 1-10 or 1-100 are all possible schemes as long as the weightings are chosen to create a meaningful overall score | [6 empty] | Enter the weights for each value in the table below. Zero if you don't want it included in the overall weighting
Must
|  | Should | [15 empty] | Yes
|  | Could |  | In | In | In | [11 empty] | No
|  | Won't |  | Out | Out | Out | [11 empty] | Maybe
| Play with in/out to model the impact on delivery of scope change | [5 empty] | Business Strategy Scores |  |  |  | Product Strategy Scores | [5 empty] | Final Weighting | Other |  |  | Business Strategy Scores |  |  |  | Product Strategy Scores
ID | Item | MoSCoW | Effort (MD) | Option A | Option B | Option C | Criteria 1 | Criteria 2 | Criteria 3 | Criteria 4 | Quality | Peformance | price reduction | Supportability | Usability | Architecture |  | Generic | Candidate for Accelerated? | Candidate for Extended? | Criteria 1 | Criteria 2 | Criteria 3 | Criteria 4 | Quality | Peformance | price reduction | Supportability | Usability | Architecture
1 | Feature 1 | Must | 60 | In | Out | Out | 0 | 10 | 9.2222 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 492.2222 |  |  |  | 5 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
2 | Feature 2 | Must | 80 | In | Out | Out | 0 | 10 | 8.7778 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 487.7778 | Yes
3 | Feature 3 | Must | 5 | In | In | In | 0 | 9 | 9.5556 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 545.5556 | Yes
4 | Feature 4 | Must | 40 | In | In | In | 0 | 10 | 8.6667 | 9 | 0 | 0 | 0 | 10 | 0 | 0 | 476.6667 |  |  | Yes
5 | Feature 5 | Must | 20 | In | In | In | 0 | 10 | 7.3333 | 9.5 | 0 | 0 | 0 | 10 | 9 | 0 | 558.3333 | Yes
6 | Feature 6 | Won't | 7 | Out | Out | Out | 0 | 10 | 7.3333 | 8.5 | 0 | 0 | 0 | 10 | 0 | 0 | 458.3333 | Yes
7 | Feature 7 | Must | 5 | In | In | In | 0 | 8 | 9.6667 | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 426.6667 |  |  | Yes
8 | Feature 8 | Must | 20 | In | Out | In | 0 | 9 | 7.25 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 432.5 |  |  | Yes
9 | Feature 9 | Must | 20 | In | Out | In | 0 | 10 | 6.5556 | 9 | 0 | 0 | 0 | 10 | 0 | 0 | 455.5556 | Yes
10 | Feature 10 | Must | 5 | In | In | In | 0 | 8 | 8 | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 410 | Yes
11 | Feature 11 | Must | 5 | In | In | In | 0 | 9.1 | 7.5 | 8 | 0 | 0 | 0 | 9.1 | 0 | 0 | 428 | Yes
12 | Feature 12 | Must | 20 | In | In | In | 0 | 8 | 6.6 | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 396 | Yes
13 | Feature 13 | Must | 20 | In | In | In | 0 | 9 | 7.3333 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 433.3333 |  | Yes
14 | Feature 14 | Won't | 60 | Out | Out | Out | 0 | 10 | 4.875 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 448.75 |  | Yes
15 | Feature 15 | Could | 20 | In | In | In | 0 | 9 | 4 | 8 | 0 | 0 | 0 | 9 | 0 | 0 | 390 |  | Yes
16 | Feature 16 | Must | 20 | In | Out | In | 0 | 6 | 9.2222 | 6 | 0 | 0 | 0 | 6 | 5 | 0 | 382.2222 |  | Yes
17 | Feature 17 | Must | 0 | In | Out | In | 0 | 6 | 8.3333 | 7 | 0 | 0 | 0 | 6 | 0 | 0 | 333.3333 |  | Yes
18 | Feature 18 | Could | 20 | Out | Out | Out | 0 | 5 | 8 | 7.5 | 0 | 0 | 0 | 5 | 0 | 0 | 305 |  | Yes
19 | Feature 19 | Must | 5 | In | In | In | 0 | 8 | 7.1111 | 7 | 0 | 0 | 0 | 8 | 0 | 0 | 381.1111 |  | Yes
20 | Feature 20 | Must | 5 | In | Out | In | 0 | 7 | 8.1111 | 3.5 | 7 | 0 | 0 | 7 | 0 | 0 | 396.1111 |  | Yes
21 | Feature 21 | Could | 5 | In | In | In | 0 | 7 | 6.2222 | 6 | 0 | 0 | 0 | 7 | 0 | 0 | 332.2222 |  | Yes
22 | Feature 22 | Could | 20 | In | Out | In | 0 | 6 | 7.8889 | 6 | 5 | 0 | 0 | 6 | 0 | 0 | 368.8889 |  | Yes
23 | Feature 23 | Could | 40 | In | Out | In | 0 | 7 | 4.875 | 8 | 0 | 0 | 0 | 7 | 0 | 0 | 338.75 |  | Yes
24 | Feature 24 | Won't | 20 | Out | Out | Out | 0 | 5 | 6.5556 | 7 | 0 | 0 | 0 | 5 | 0 | 0 | 285.5556 |  | Yes
25 | Feature 25 | Must | 40 | In | In | In | 0 | 5 | 8 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 280 |  | Yes
26 | Feature 26 | Must | 20 | In | In | In | 0 | 8 | 6 | 5 | 0 | 0 | 0 | 8 | 0 | 0 | 350 |  | Yes
27 | Feature 27 | Could | 20 | In | In | In | 0 | 5 | 7.6667 | 7.5 | 0 | 0 | 0 | 5 | 0 | 0 | 301.6667 |  | Yes
28 | Feature 28 | Won't |  | Out | Out | Out | 0 | 5 | 8.3333 | 6 | 5 | 0 | 0 | 5 | 0 | 0 | 343.3333 |  | Yes
29 | Feature 29 | Won't |  | Out | Out | Out | 0 | 4 | 6.3333 | 6 | 0 | 0 | 0 | 4 | 0 | 0 | 243.3333 | yes
30 | Feature 30 | Must | 5 | In | In | In | 0 | 5 | 5.5714 | 6.5 | 0 | 0 | 0 | 5 | 0 | 0 | 270.7143 | Yes
31 | Feature 31 | Could | 20 | Out | Out | Out | 0 | 5 | 6.5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 265 | Yes
32 | Feature 32 | Won't | 20 | Out | Out | Out | 0 | 5 | 3.2857 | 8 | 0 | 0 | 0 | 5 | 0 | 0 | 262.8571 |  | Yes
33 | Feature 33 | Could | 20 | Out | Out | Out | 0 | 8 | 5.8889 | 4.5 | 0 | 0 | 0 | 8 | 0 | 0 | 343.8889 |  | Yes
34 | Feature 34 | Must | 5 | In | In | In | 0 | 5 | 5.5 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 305 | Yes
35 | Feature 35 | Must | 20 | In | In | In | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 250 | Yes
36 | Feature 36 | Must | 1 | In | In | In | 10 | 5 | 5.625 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 296.25 | Yes
37 | Feature 37 | Won't |  | Out | Out | Out | 0 | 5 | 5.5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 255 | Yes
38 | Feature 38 | Could | 5 | Out | Out | Out | 0 | 4 | 4.25 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 212.5
39 | Feature 39 | Should | 5 | In | In | In | 0 | 4 | 3.75 | 5 | 0 | 0 | 0 | 4 | 5 | 0 | 257.5 | Yes
40 | Feature 40 | Won't |  | Out | Out | Out | 0 | 5 | 4.5714 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 245.7143
41 | Feature 41 | Should | 20 | In | In | In | 0 | 2 | 7 | 4 | 0 | 0 | 0 | 2 | 6 | 0 | 230 | Yes
42 | Feature 42 | Won't |  | Out | Out | Out | 0 | 5 | 4.625 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 236.25 | Yes
43 | Feature 43 | Won't |  | Out | Out | Out | 0 | 4 | 4.25 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 212.5 | Yes
44 | Feature 44 | Won't | 20 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
45 | Feature 45 | Should | 60 | In | In | In | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 50 | Yes
46 | Feature 46 | Should | 20 | In | In | In | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
47 | Feature 47 | Should | 20 | In | In | In | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Yes
48 | Feature 48 | Won't | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
49 | Feature 49 | Won't | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | 1 | Out | Out | Out | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Item |  | Effort (MD) | In/Out | In/Out | In/Out | Criteria 1 | Criteria 2 | Criteria 3 | Criteria 4 | Quality | Peformance | price reduction | Supportability | Usability | Architecture | Final Weighting | Generic | Candidate for Accelerated? | Candidate for Extended?
| Totals |  |  | 651 | 386 | 511 | 10 | 210.1 | 206.3381 | 208 | 17 | 0 | 0 | 210.1 | 39 | 0 | 11056.381 | 291 | 215 | 85
|  |  | enter daily rate-> | 500 | 500 | 500
|  |  | enter QA cost multiplier; typically 1.2 to 1.5-> | 1.4 | 1.4 | 1.4
| Release Cost |  |  | 455700 | 270200 | 357700
| MoSCoW Totals | Total | In Scope | As % of total Musts, Shoulds etc
| Must | 22 | 22 | 100%
| Should | 5 | 5 | 100%
| Could | 9 | 5 | 55.56%
| Won't | 13 | 0 | 0%
| The charts below refer to the first option column above i.e. | [6 empty] | Option A
Note - first 60 features only included in table above
Greens are strong candidates, Reds are out, and yellows are worth considering
Note on R8: Calculated using values in weighting table to the right
Note on T9: Is this a roadmap feature (or potential roadmap feature) which a customer might pay to have brought forward?
Note on U9: Is this feature a customer specific feature which they might be prepared to pay for?

## Resource Model
Enter week commencing dates, resource names, efficiency and % availability week by week. Expended man days and required man days are calculated
Allocation per week
Resource | Comment | Profile 1 Efficiency | Profile 2 Efficiency | Profile 3 Efficiency | time axis 2008-10-01 to 2010-03-10
Person 1 |  | 0.75 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 2 |  | 0.75 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 3 |  | 0.75 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 4 |  | 0.75 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 5 |  | 0.75 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 6 |  | 0 | 0.75 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 7 |  | 0 | 0 | 0.75 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 8 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 9 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 10 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 11 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 12 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 13 |  | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Person 14 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 15 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 16 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 17 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 18 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 19 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 20 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 21 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 22 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 23 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 24 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 25 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 26 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Person 27 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 1 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 2 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 3 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 4 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 5 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
new hire 6 |  | 0 | 0 | 0 | bar: 2008-10-01 to 2010-03-10
Total MD |  | 3.75 | 4.5 | 5.25 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 0 | 0 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 0 | 0 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75 | 18.75
|  |  |  | Resource Profile 1 | 18.75 | 37.5 | 56.25 | 75 | 93.75 | 112.5 | 131.25 | 150 | 168.75 | 187.5 | 206.25 | 225 | 225 | 225 | 243.75 | 262.5 | 281.25 | 300 | 318.75 | 337.5 | 356.25 | 375 | 393.75 | 412.5 | 431.25 | 450 | 468.75 | 487.5 | 506.25 | 525 | 543.75 | 562.5 | 581.25 | 600 | 618.75 | 637.5 | 656.25 | 675 | 693.75 | 712.5 | 712.5 | 712.5 | 731.25 | 750 | 768.75 | 787.5 | 806.25 | 825 | 843.75 | 862.5 | 881.25 | 900 | 918.75 | 937.5 | 956.25 | 975 | 993.75 | 1012.5 | 1031.25 | 1050 | 1068.75 | 1087.5 | 1106.25 | 1125 | 1143.75 | 1162.5 | 1181.25 | 1200 | 1218.75 | 1237.5 | 1256.25 | 1275 | 1293.75 | 1312.5 | 1331.25 | 1350
|  |  |  | Resource Profile 2 | 22.5 | 45 | 67.5 | 90 | 112.5 | 135 | 157.5 | 180 | 202.5 | 225 | 247.5 | 270 | 270 | 270 | 292.5 | 315 | 337.5 | 360 | 382.5 | 405 | 427.5 | 450 | 472.5 | 495 | 517.5 | 540 | 562.5 | 585 | 607.5 | 630 | 652.5 | 675 | 697.5 | 720 | 742.5 | 765 | 787.5 | 810 | 832.5 | 855 | 855 | 855 | 877.5 | 900 | 922.5 | 945 | 967.5 | 990 | 1012.5 | 1035 | 1057.5 | 1080 | 1102.5 | 1125 | 1147.5 | 1170 | 1192.5 | 1215 | 1237.5 | 1260 | 1282.5 | 1305 | 1327.5 | 1350 | 1372.5 | 1395 | 1417.5 | 1440 | 1462.5 | 1485 | 1507.5 | 1530 | 1552.5 | 1575 | 1597.5 | 1620
|  |  |  | Resource Profile 3 | 26.25 | 52.5 | 78.75 | 105 | 131.25 | 157.5 | 183.75 | 210 | 236.25 | 262.5 | 288.75 | 315 | 315 | 315 | 341.25 | 367.5 | 393.75 | 420 | 446.25 | 472.5 | 498.75 | 525 | 551.25 | 577.5 | 603.75 | 630 | 656.25 | 682.5 | 708.75 | 735 | 761.25 | 787.5 | 813.75 | 840 | 866.25 | 892.5 | 918.75 | 945 | 971.25 | 997.5 | 997.5 | 997.5 | 1023.75 | 1050 | 1076.25 | 1102.5 | 1128.75 | 1155 | 1181.25 | 1207.5 | 1233.75 | 1260 | 1286.25 | 1312.5 | 1338.75 | 1365 | 1391.25 | 1417.5 | 1443.75 | 1470 | 1496.25 | 1522.5 | 1548.75 | 1575 | 1601.25 | 1627.5 | 1653.75 | 1680 | 1706.25 | 1732.5 | 1758.75 | 1785 | 1811.25 | 1837.5 | 1863.75 | 1890
|  |  |  | Option A | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651
|  |  |  | Option B | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386 | 386
|  |  |  | Option C | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511 | 511
|  | w/c | w/c | w/c | time axis 2008-10-01 to 2010-03-10
Note on C4: value between 0 and 1 reflecting experience and output of each individual
Note on D4: value between 0 and 1 reflecting experience and output of each individual
Note on E4: value between 0 and 1 reflecting experience and output of each individual
Note on F4: set the first day of the project and the row should update itself
Note on A32: Sheila McWilliams: Have assumed that this new hire will be on installers or given to Ian in place of Dermot / Pearse.

## Timelines
Option | 2008 | [11 empty] | 2010
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
A | Q4 Nov: Release
B | Q3 Sep: First Release; Q1 Jan: Version 2
C | Q3 Aug: First Release; Q4 Dec: Version 2
D | bar: Q1 Jan to Q2 May; Q3 Sep to Q2 Jun
Target for demo in Vegas

## Payback Period
Forecast | Sunk Cost | Variable Cost | Price | Year 1 units | Year 2 units | Year 3 units | Year 4 units | Year 5 units
Low | 450000 | 700 | 1200 | 200 | 200 | 200 | 200 | 200
|  |  | Cost | 590000 | 730000 | 870000 | 1010000 | 1150000
|  |  | Revenue | 240000 | 480000 | 720000 | 960000 | 1200000
|  |  | Margin | -145.8% | -52.08% | -20.83% | -5.208% | 4.167%
Medium | 450000 | 700 | 1200 | 450 | 450 | 450 | 450 | 450
|  |  | Cost | 765000 | 1080000 | 1395000 | 1710000 | 2025000
|  |  | Revenue | 540000 | 1080000 | 1620000 | 2160000 | 2700000
|  |  | Margin | -41.67% | 0% | 13.89% | 20.83% | 25%
High | 450000 | 700 | 1200 | 600 | 600 | 600 | 600 | 600
|  |  | Cost | 870000 | 1290000 | 1710000 | 2130000 | 2550000
|  |  | Revenue | 720000 | 1440000 | 2160000 | 2880000 | 3600000
|  |  | Margin | -20.83% | 10.42% | 20.83% | 26.04% | 29.17%